## Feuille 1
EACH MEMBER
Have something to discuss about the core features (Search properties, requests visits, CRUD op. on properties, CRUD operations on brokers)
Discuss originality and innovation, how can we make this different?
background for the readme file team section
Detailed log of each team member's contribution including time spent for each activity
TASKS
Where | What | Who | Dependencies | notes
Roles | Team Leader &Scrum master | Dominique
Roles | Secretary & Development team | Isabelle
Roles | Development team | Rebecca
Roles | Development team | Taylor
Roles | Development team | Junior
GITHUB | Create repository | Isabelle
GITHUB | Create sprint folders | Dominique
GITHUB | Keep github organized and make sure the files are in the right folders | Dominique
Repository about section - Github | Add description to the repository | Isabelle
Readme File - Github | Team member section | Isabelle | Need everybody's background
Readme File - Github | Project descriptioon | Rebecca
Readme File - Github | Installation instruction | Rebecca
Readme File - Github | Usage Guidelines | Rebecca
Readme File - Github | Reference to Wiki | Dominique
Wiki - Github | Plan for next sprint | Dominique
Wiki - Github | Project approach and technologies - Agile approach | Junior |  | Done
Wiki - Github | Project approach and technologies - Technology stack | Taylor |  | Done
Wiki - Github | Project approach and technologies - Technology stack rationale | Taylor |  | Done
Training and research | Research on technologies and set up environment for sprint #2 | Taylor |  | Research and advice the team on best technologies to use. Team discussion and decisions based on these research held on sept 21 2023.
Sprint #1 Subfolder - Github | Sprint #1 backlog | Dominique
Sprint #1 Subfolder - Github | User Stories #1 | Rebecca |  | People working on the user stories -> coordinate
Sprint #1 Subfolder - Github | User Stories #2 | Rebecca |  | User stories based on project backlog and features
Sprint #1 Subfolder - Github | User Stories #3 | Isabelle
Sprint #1 Subfolder - Github | User Stories #4 | Isabelle
Sprint #1 Subfolder - Github | Task Breakdown | Dominique | Depends on user stories | Story points?
Sprint #1 Subfolder - Github | Gathering the detail logs and making a file out of it + adding it to the subfolder | Dominique
Sprint #1 Subfolder - Github | Metting minutes #1 | Dominique
Sprint #1 Subfolder - Github | Meeting minutes # 2 to #8 (end of srpint #1) | Isabelle
Sprint #1 Subfolder - Github | Project Reports | Dominique |  | I will ask TA tro clarify this one
Sprint #1 Subfolder - Github | Project Backlog | Dominique |  | started / draft in google drive