## Sheet1
SPRINT 3
Issue # from your repository. | From top user story | User story/Task title | Story points associated to a US/task | Due date | Dependencies | Task description | Priority (low, medium, high) | Risk (low, medium, high) | Responsible
#131 | US-1 | US-1.4 Homebuyers Search for brokers | 40 | 10/11/2023 | Dependencies | As a Homebuyer or Guest , I want to have a search page where I can find a broker so that I can Buy or Sell my house using their services. | HIGH | medium | Broke Brokers
#132 | US-1.4 | TASK - 1.4.1 Mockup for search for brokers page | 3 | 10/11/2023 | 0 | As a development team, I want to follow a mockup of the page so that I can follow the design choices made for the page . | MEDIUM | low | Isabelle, Rebecca
#133 | US-1.4 | TASK - 1.4.2 Add the search for broker page to homebuyer,renter and guest navigation bar | 1 | 10/11/2023 | 1.4.1 | As a Homebuyer, Renter or guest I want to to have a "search for broker" button in the top navigation bar so that I can access the broker search page . | HIGH | medium | Junior
#134 | US-1.4 | TASK - 1.4.3 Create Search-for-Broker.js page and route from App.js | 1 | 10/11/2023 | 1.4.1 | As a development team, I want to have a search-for-broker.js page created to a so that I can add components to it . As a development team, I want to have a route to the search-for-broker.js page in the url | HIGH | low | Dominique
#136 | US-1.4 | TASK - 1.4.4 Login prompts from search for brokers | 2 | 10/11/2023 | 1.4.1 | As a homebuyer, renter or guest, I want to be prompt to login so that I can browser brokers and send email from my account. | Medium | medium | Taylor
#137 | US-1.4 | TASK - 1.4.5 Search-for-brokers page gallery | 4 | 10/11/2023 | 1.4.1 | As a homebuyer,renter or guest, I want to see broker information cards displayed in a gallery so that I can visualise who I want to contact . | HIGH | medium | Taylor
#138 | US-1.4 | TASK - 1.4.6 Search for brokers Search bar and filters | 5 | 10/11/2023 | 1.4.7 | As a homebuyer, renter or guest, I want to enter search criteria and check filter options so that see the brokers matching my choices in the gallery . | HIGH | medium | Taylor
#139 | US-1.4 | TASK - 1.4.7 Add brokers fields to brokers database | 4 | 10/11/2023 | 0 | As development team, I want to add certain fields to the database so that I can fetch them in the search for brokers page . | MEDIUM | high | Rebecca
#140 | US-1.4 | TASK - 1.4.8 contact brokers form | 5 | 10/11/2023 | 1.4.5, 1.4.1 | As a Homebuyer, or renter, I want to fill up a form so that a broker receives an email asking to contact me . | HIGH | medium | Junior
#141 | US-1.4 | TASK - 1.4.9 brokers contact email sent + confirmation email to user | 4 | 10/11/2023 | 1.4.8, 1.4.1 | As a homebuyer or renter, I want the form I filled to send an email to the broker so that I can be called back . As a homebuyer or renter, I want to get a confirmation email so that I know that my contact request has been submitted | MEDIUM | medium | Dominique
#159 | US-1.4 | TASK - 1.4.12 Create Brokers-Client.js page and route from App.js | 1 | 10/11/2023 |  | As a development team, I want to have a Brokers-clients.js page created to a so that I can add components to it . | MEDIUM | low | Dominique
#158 | US-1.4 | TASK - 1.4.10 Brokers CRUD to clients | 4 | 10/11/2023 | 1.4.1,1.4.12 | As a broker I want to be able to read, create , edit and delete clients after they contacted me through the search for broker feature so that I can manage my list of client | MEDIUM | medium | Dominique
#157 | US-1.4 | TASK - 1.4.11 All database links done for 1.4 | 6 | 10/11/2023 | 1.4.10 | As a development team I want to link all the database requests of frontent to backend so the proper information is retrieved. | HIGH | high | Rebecca
#135 | US-2 | US-2.4 Renters Search for brokers | 0 | 10/11/2023 | 1.4 | As a renter , I want to have a search page where I can find a broker so that I can Buy or Sell my house using their services. | MEDIUM | low | Broke Brokers
|  | tasks are all the same as 1.4 |  | 10/11/2023
#143 | US-3 | US- 3.1 Brokers Submit Offers | 28 | 10/11/2023 |  | As a Broker, I want to submit offers on houses for sale so that my client can buy the house if their offer is accepted. | HIGH |  | Broke Brokers
#144 | US- 3.1 | TASK - 3.1.1 Mockup for submit offer feature | 3 | 10/11/2023 |  | As a development team, I want to follow a mockup of the submit offer feature so that I can follow the design choices made\ . | MEDIUM | low | Isabelle, Rebecca
#145 | US- 3.1 | TASK - 3.1.2 Brokers navigation Bar | 3 | 10/11/2023 | 3.1.1 | As a broker I want to see the right navigations buttons so I can perform my tasks on the website. | MEDIUM | medium | Junior
#146 | US- 3.1 | TASK - 3.1.3 Make an Offer on this house button in property page | 2 | 10/11/2023 | 3.1.1 | As a broker I want to click on a button on the property page so that I can make an offer on this property on behalf of my clients | HIGH | low | Dominique
#147 | US- 3.1 | TASK - 3.1.4 Offer on property form | 5 | 10/11/2023 | 3.1.1 , 3.1.3 | As a broker, I want to fill a form so that I can make an offer on a house on behalf of my client . | HIGH | medium | Junior
#148 | US- 3.1 | TASK - 3.1.5 Make offer on house confirmation emails | 4 | 10/11/2023 | 3.1.2 | As a broker, I want to send a confirmation email to my client once I filled the make an offer on a house form so that my client knows it's been done and what info were in the offer . | LOW | medium | Isabelle
#149 | US- 3.1 | TASK - 3.1.6 Update "offer sent" section of broker "offer" page | 5 | 10/11/2023 | 3.1.3 | As a broker, I want the "offer sent" section of my "offer" page to update so that I can see a list of the offers I sent . | MEDIUM | high | Taylor
#160 | US- 3.1 | TASK - 3.1.7 All database links done for 3.1 | 6 | 10/11/2023 | 3.1.4,3.1.6 | As a development team I want to link all the database requests of frontent to backend so the proper information is retrieved. | MEDIUM | high | Rebecca
#142 | US-3 | US- 3.5 Offer Management | 33 | 10/11/2023
#150 | US- 3.5 | TASK - 3.5.1 Mockup for Offer Management | 3 | 10/11/2023 |  | As a development team, I want to follow a mockup of the manage offer feature so that I can follow the design choices made\ . | MEDIUM | low | Isabelle, Rebecca
#151 | US- 3.5 | TASK - 3.5.2 Add new offer notification button ton navigation bar | 3 | 10/11/2023 | 3.1.2, 3.1.1 | As a broker, I want a red circle over the offer page navigation bar button so that I can see that I have unseen offers | LOW | high | Junior
#152 | US- 3.5 | TASK - 3.5.3 Create Broker- offers.js page and route from App.js | 1 | 10/11/2023 |  | As a development team, I want to have a Brokers-offer.js page created to a so that I can add components to it . | HIGH | medium | Dominique
#153 | US- 3.5 | TASK - 3.5.4 Broker-offers page "offer received" section | 5 | 10/11/2023 | 3.5.3,3.1.2 | As a broker I want to see a section of all the offers I received in my offer page so that I accept,reject or negociate the offer. | HIGH | medium | Taylor
#154 | US- 3.5 | TASK - 3.5.5 Broker-offers page "offer sent" section | 5 | 10/11/2023 | 3.5.3,3.1,2 | As a broker I want to see a section of all the offers I sent in my offer page so that I can keep track of these offers. | HIGH | medium | Taylor
#155 | US- 3.5 | TASK - 3.5.6 Broker-offers page "past received" and "past sent" sections | 4 | 10/11/2023 | 3.5.3,3.1.2 | As a broker I want to see sections of all my past received and past sent offers in my offer page so that I can look back on them. | LOW | medium | Taylor
#156 | US- 3.5 | TASK - 3.5.6 Emails : email client on offer received + automatic email after accept or rejet offer or negociation | 6 | 10/11/2023 | 3.1.2,3.5.4,3.5.5 | As a broker, I want to send an automatic emails when I accept or reject an offer received so that I can let the buyer know the clients decision and let my clients know I let the buyer know of the decision | LOW | medium | Rebecca
#160 | US- 3.5 | TASK - 3.5.7 All database links done for 3.5 | 6 | 10/11/2023 | 3.5.2,3.5.4,3.5.5,3.5.6 | As a development team I want to link all the database requests of frontent to backend so the proper information is retrieved. | HIGH | high | Rebecca
#162 |  | Meeting minutes sprint 3 | 6 | 10/11/2023 |  | As a development team member, I want to log the meeting minutes discussions and decisions items to github so that we can keep track of them | HIGH | low | Isabelle
#163 |  | Sprint backlog sprint 4 | 6 | 10/11/2023 |  | As members of the development team, we want to create te sprint 4 backlog so we know the features and tasks that we will have to do in sprint #4 | HIGH | low | Dominique