## Sheet1
TASK ID | TASK NAME | DEPENDENCY | START | FINISH | As a | I want to | So that | STORY | Assigned to | STATUS | STORY POINTS
Sprint 2 Start : User stories #1 -2 - 6
22 | Web app mockup |  | 2023-09-29 | 2023-10-27 | [6 empty] | 1
22.1 | login page
22.2 | search
22.3 | properties visual
22.4 | brokers menu
22.5 | syste adminitrator menu
23 | Property databases to search from created and populated | Task 12 | 2023-09-29 | 2023-10-27 |  |  |  | 1 |  |  | 2
23.1 | property database field established
23.2 | property database created
23.3 | property database populated
24 | Broker's database created and populated |  | 2023-09-29 | 2023-10-27 |  |  |  | 3 |  |  | 2
24.1 | brokers database field established
24.2 | brokers database created
24.3 | brokers database populated
25 | Homebuyers + renters database created and populated | Task 12 and 13 (User stories) | 2023-09-29 | 2023-10-27 |  |  |  | 1 and 2 |  |  | 2
25.1 | Homebuyers/Renters database field established
25.2 | Homebuyers/Renters database created
25.3 | Homebuyers/Renters database populated
26 | Brading guide |  | 2023-09-29 | 2023-10-27 | [6 empty] | 2
26.1 | color palette
26.2 | typography
26.3 | style of button
26.4 | tone
27 | HTML website structure + navigation | Task 22 | 2023-09-29 | 2023-10-27 | [6 empty] | 5
27.1
27.2
30 | User Story #1 - Homebuyers Implemented | Task 12 | 2023-09-29 | 2023-10-27 |  |  |  | 1 |  |  | 5
30.1 |  |  |  |  | As a Homebuyer | I want to search properties by value | So that I can find properties in my affodable range
30.2
30.3
30.4
31 | Database link to frontend |  | 2023-09-29 | 2023-10-27 | [6 empty] | 5
32 | Website frame refactoring |  | 2023-09-29 | 2023-10-27 | [6 empty] | 4
33 | Testing of website Frame |  | 2023-09-29 | 2023-10-27 | [6 empty] | 2
34 | Testing of Homebuyers feature | Task 12 | 2023-09-29 | 2023-10-27 |  |  |  | 1 |  |  | 2
35 | User Story #2 Renters features implemented | Task 13 | 2023-09-29 | 2023-10-27 |  |  |  | 2 |  |  | 5
36 | Testing of User Story #2 Renters features | Task 13 | 2023-09-29 | 2023-10-27 |  |  |  | 2 |  |  | 2
37 | Refactoring after Homebuyers feature |  | 2023-09-29 | 2023-10-27 |  |  |  | 1 |  |  | 4
38 | Refactoring after renters feature |  | 2023-09-29 | 2023-10-27 |  |  |  | 2 |  |  | 4
39 | Implementation of feature User story or #6 | Task 29 | 2023-09-29 | 2023-10-27 |  |  |  | 6 |  |  | 5
50 | User Story #3 -Brokers CRUD Implementation | Task 14 | 2023-10-27 | 2023-11-10 |  |  |  | 3 |  |  | 3
51 | Testing of User Story #3(Brokers CRUD) implementation | Task 14 | 2023-10-27 | 2023-11-10 |  |  |  | 3 |  |  | 3
52 | Refactoring after User Story #3 Implementation |  | 2023-10-27 | 2023-11-10 |  |  |  | 3 |  |  | 4
53 | User Story #4 -System Admin CRUD Implemented | Task 15 | 2023-10-27 | 2023-11-10 |  |  |  | 4 |  |  | 5
54 | Testing of User Story #4 -System Admin CRUD) implementation | Task 15 | 2023-10-27 | 2023-11-10 |  |  |  | 4 |  |  | 3
55 | Refactoring after User Story #4 -System Admin CRUD |  | 2023-10-27 | 2023-11-10 |  |  |  | 4 |  |  | 4
40 | Final test of features |  | 2023-09-29 | 2023-10-27 | [6 empty] | 3
41 | Contribution logs |  | 2023-09-29 | 2023-10-27 | [6 empty] | 2
42 | End of sprint 2 : review of github organisation |  | 2023-09-29 | 2023-10-27 | [6 empty] | 1
43 | sprint 2 meeting minutes |  | 2023-09-29 | 2023-10-27 | [6 empty] | 3
44 | Review and add new information to wiki |  | 2023-09-29 | 2023-10-27 | [6 empty] | 2
45 | Review and add new information to README |  | 2023-09-29 | 2023-10-27 | [6 empty] | 2
46 | End of sprint meeting |  | 2023-09-29 | 2023-10-27 | [6 empty] | 1